VISTA Host Site Application Timeline

Phase I – Site Selections:

| Due Dates | Activity |
| --- | --- |
| October 14, 2025 | AmeriCorps Info Session at 10am (MT) |
| October 14, 2025 | VISTA Application Opens |
| October 21, 2025 | Intent to Apply form due by 4 PM (MT) |
| October 21, 2025 | Office Hours: 10 AM (MT) (Optional) |
| November 14, 2025 | VISTA Host Site Application due to Serve Idaho by 4 PM (MT) |
| November 17, 2025 | Applications Sent to Reviewers |
| Week of December 8, 2025 | GARP Application Review |
| December 19, 2025 | Clarification Letters Sent to Applicants |
| January 6, 2026 | Clarification Responses due by 4 PM (MT) |
| January 15, 2026 | Full Serve Idaho Commission VISTA Host Site approval |
| January 20, 2026 | Notification of Site Selection and MOA Provided to Host Sites |

Phase II – Project Launch:

| Date Dates | Activity |
| --- | --- |
| January 20, 2026 | Serve Idaho Inputs Grants into the eGrants platform |
| January 27, 2026 | Required Host Site training at 10am (MT) on Teams (virtual): developing your VISTA Assignment Description (VAD), Service Opportunity Listing (SOL), Onsite Orientation and Training (OSOT) |
| February 6, 2026 | VAD and SOL due to Serve Idaho by 4pm (MT) Entered into eGrants OR Returned to Host Sites with Edits and Feedback |
| February 20, 2026 | MOA due to Serve Idaho by 4pm (MT) |
| February 27, 2026 | Onsite Orientation and Training (OSOT) due to Serve Idaho by 4 PM (MT) |

FOR MORE INFORMATION CONTACT:

Project Coordinator, Micaela de Loyola-Carkin, Micaela.deloyola-carkin@labor.idaho.gov